## Ownership_PI_Tracker
Epic Name | Activity | Primary Owners | Secondary Owners | Sprint | Status | Progress % | Notes | JIRA Epic Link
Qlik Support | Support existing Qlik applications: daily/monthly refreshes, incident resolution, tickets | Qlik Devs | MSTR Devs | PI1-S1 | Not Started | 0
MSTR Regular Support | BAU MicroStrategy support: Autosys jobs, subscriptions, reference file loads, CI/CD migrations | MSTR Devs | Qlik Devs | PI1-S1 | Not Started | 0
MSTR Admin & Adhoc Support | Admin-level MicroStrategy support: user management, adhoc fixes, infra escalations | MSTR Admin/Lead | Cloud SME | PI1-S2 | Not Started | 0
MSTR Development (incl. Qlik→MSTR Conversion) | New MicroStrategy development (dashboards, metrics) + Qlik→MSTR conversion | MSTR Devs | Qlik Devs | PI1-S2 | Not Started | 0
Cloud Development for Reporting & Analytics | Cloud-native development: SIP modernization, Databricks ETL, pipeline orchestration, Glue/Athena models | Cloud SME + MSTR Devs | Qlik Devs | PI1-S3 | Not Started | 0
Cloud Support for Reporting & Analytics | Cloud support: monitor existing AWS/Databricks/Glue pipelines, job failures, refresh stability | Cloud SME + Support Devs | MSTR Devs | PI1-S4 | Not Started | 0